## Slide 1: Scheduling: CrossChek Golf Club Manufacturing
CrossChek sporting goods is considering a process for development of a new golf club
Processing times, as well as constraints over when each step in the process can start are given in the next slide
CrossChek would like to have a few questions about the process answered:
  How long does the process take (i.e. the least amount of time)?
  What are the scheduled start and end times for each activity?
  Which activities are critical? That is, which activities must be completed on time to keep the project on schedule?
  For how long can non-critical activities be delayed?

## Slide 2: Scheduling Golf Club Production
Activity | Description | Predecessors | Time (days)
A | Planning | -- | 10
B | Club face forging | A | 8
C | Shaft construction | A | 14
D | Club head manufacturing | B, C | 8
E | Gripping | C | 7
F | Assembly | D, E | 12
G | Balancing | F | 10

## Slide 3: The Critical Path Method (CPM)
How can we answer these questions:
  How long does the process take (i.e. the least amount of time)?
  What are the scheduled start and end times for each activity?
  Which activities are critical? That is, which activities must be completed on time to keep the project on schedule?
  For how long can non-critical activities be delayed?

## Slide 4: The Critical Path Method (CPM)
For each activity, let:
  t: the time it takes to complete
  ES: the earliest start time
  EF: the earliest finish time
  LS: the latest start time
  LF: the latest finish time
Create a predecessor graph, called a project graph
One node for each activity:
Activity | ES | EF
t | LS | LF

## Slide 5: The Critical Path Method (CPM)
“Slack” or “Float”
  The amount of time an activity can be delayed without affecting the overall project completion time
Computed by LS – ES or LF – EF
There will always be a path of activities with no float
This path is known as the critical path

## Slide 6: The Critical Path Method (CPM)
We can now answer these questions:
  How long does the process take (i.e. the least amount of time)?
    54 days
  What are the scheduled start and end times for each activity?
    See ES, EF for each activity
  Which activities are critical? That is, which activities must be completed on time to keep the project on schedule?
    Planning-Shaft construction-Club head manufacturing-Assembly-Balancing
  For how long can non-critical activities be delayed?
    Club face forging: 6 days; Gripping: 1 day

## Slide 7: Project Acceleration
CrossChek management finds that the results of the scheduling analysis are unacceptable, and that the project must be completed within 50 days. Management appreciates that project activity times can only be reduced so much, and that there will be costs associated with these reductions

## Slide 8: Crashing
Commonly used term for project acceleration
The minimum amount of time in which an activity can be completed (i.e. under maximum acceleration) is known as its crash time
The per-unit cost of accelerating an activity is known as its crash cost

## Slide 9: Project Acceleration for CrossChek
Activity | Description | Predecessors | Time | Crash Time | Crash Cost (1000’s)
A | Planning | -- | 10 | 8 | 400
B | Club face forging | A | 8 | 7 | 600
C | Shaft construction | A | 14 | 10 | 300
D | Club head manufacturing | B, C | 8 | 5 | 100
E | Gripping | C | 7 | 3 | 200
F | Assembly | D, E | 12 | 9 | 300
G | Balancing | F | 10 | 8 | 500

## Slide 10: LP for CrossChek Crashing Problem
Min 400yA + 600yB + 300yC + 100yD + 200yE + 300yF + 500yG
st
xA + yA > 10
xB + yB - xA > 8
xC + yC - xA > 14
xD + yD - xB > 8
xD + yD - xC > 8
xE + yE - xC > 7
xF + yF - xD > 12
xF + yF - xE > 12
xG + yG - xF > 10
yA < 2
yB < 1
yC < 4
yD < 3
yE < 4
yF < 3
yG < 2
xG < 50

## Slide 11: LINDO Solution
VARIABLE VALUE REDUCED COST
YA 0.000000 100.000000
YB 0.000000 600.000000
YC 0.000000 0.000000
YD 3.000000 0.000000
YE 2.000000 0.000000
YF 1.000000 0.000000
YG 0.000000 200.000000
XA 10.000000 0.000000
XB 24.000000 0.000000
XC 24.000000 0.000000
XD 29.000000 0.000000
XE 29.000000 0.000000
XF 40.000000 0.000000
XG 50.000000 0.000000