## Slide 1: PERT
“Program Evaluation and Review Technique”
Very similar to CPM
Key difference: activity times may be uncertain
Analysis is more time-based i.e. how likely we are to finish in a certain amount of time, as opposed to cost-based (i.e. as with CPM)

## Slide 2: Uncertain Activities Times
CrossChek cannot ensure that the activity times for each task will be exact
Rather, they can merely specify:
  An optimistic time
  A most probable time
  A pessimistic time
These estimates are given in the following table:

## Slide 3: Uncertain Activities Times
Activity | Predecessors | Optimistic | Most Probable | Pessimistic
A | -- | 7 | 10 | 19
B | A | 5 | 8 | 11
C | A | 11 | 14 | 20
D | B, C | 8 | 8 | 11
E | C | 4 | 7 | 13
F | D, E | 9 | 12 | 15
G | F | 7 | 10 | 19

## Slide 4: Uncertain Activities Times
Activity | Predecessors | Optimistic | Most Probable | Pessimistic
A | -- | 7 | 10 | 19
B | A | 5 | 8 | 11
C | A | 11 | 14 | 20
D | B, C | 8 | 8 | 11
E | C | 4 | 7 | 13
F | D, E | 9 | 12 | 15
G | F | 7 | 10 | 19
Given these values, CrossChek wants to know:
  What is the expected completion time for the project?
  What is the probability that the project will be completed in 58 days? 55 days?

## Slide 5: Expected Activity Times and Variance
Activity | Predecessors | Optimistic | Most Probable | Pessimistic | Expected | Variance
A | -- | 7 | 10 | 19 | 11 | 4
B | A | 5 | 8 | 11 | 8 | 1
C | A | 11 | 14 | 20 | 14.5 | 2.25
D | B, C | 8 | 8 | 11 | 8.5 | 0.25
E | C | 4 | 7 | 13 | 7.5 | 2.25
F | D, E | 9 | 12 | 15 | 12 | 1
G | F | 7 | 10 | 19 | 11 | 4
Given these values, CrossChek wants to know:
  What is the expected completion time for the project?
  What is the probability that the project will be completed in 58 days? 55 days?

## Slide 6
x | 0.00 | 0.01 | 0.02 | 0.03 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.09
.00 | .5000 | .5040 | .5080 | .5120 | .5160 | .5199 | .5239 | .5279 | .5319 | .5359
.10 | .5398 | .5438 | .5478 | .5517 | .5557 | .5596 | .5636 | .5675 | .5714 | .5754
.20 | .5793 | .5832 | .5871 | .5910 | .5948 | .5987 | .6026 | .6064 | .6103 | .6141
.30 | .6179 | .6217 | .6255 | .6293 | .6331 | .6368 | .6406 | .6443 | .6480 | .6517
.40 | .6554 | .6591 | .6628 | .6664 | .6700 | .6736 | .6772 | .6808 | .6844 | .6879
.50 | .6915 | .6950 | .6985 | .7019 | .7054 | .7088 | .7123 | .7157 | .7190 | .7224
.60 | .7258 | .7291 | .7324 | .7357 | .7389 | .7422 | .7454 | .7486 | .7518 | .7549
.70 | .7580 | .7612 | .7642 | .7673 | .7704 | .7734 | .7764 | .7794 | .7823 | .7852
.80 | .7881 | .7910 | .7939 | .7967 | .7996 | .8023 | .8051 | .8079 | .8106 | .8133
.90 | .8159 | .8186 | .8212 | .8238 | .8264 | .8289 | .8315 | .8340 | .8365 | .8389
1.0 | .8413 | .8438 | .8461 | .8485 | .8508 | .8531 | .8554 | .8577 | .8599 | .8621
1.1 | .8643 | .8665 | .8686 | .8708 | .8729 | .8749 | .8770 | .8790 | .8810 | .8830
1.2 | .8849 | .8869 | .8888 | .8907 | .8925 | .8944 | .8962 | .8980 | .8997 | .9015
1.3 | .9032 | .9049 | .9066 | .9082 | .9099 | .9115 | .9131 | .9147 | .9162 | .9177
1.4 | .9192 | .9207 | .9222 | .9236 | .9251 | .9265 | .9279 | .9292 | .9306 | .9319
1.5 | .9332 | .9345 | .9357 | .9370 | .9382 | .9394 | .9406 | .9418 | .9430 | .9441
1.6 | .9452 | .9463 | .9474 | .9485 | .9495 | .9505 | .9515 | .9525 | .9535 | .9545
1.7 | .9554 | .9564 | .9573 | .9582 | .9591 | .9599 | .9608 | .9616 | .9625 | .9633
1.8 | .9641 | .9649 | .9656 | .9664 | .9671 | .9678 | .9686 | .9693 | .9700 | .9706
1.9 | .9713 | .9719 | .9726 | .9732 | .9738 | .9744 | .9750 | .9756 | .9762 | .9767
2.0 | .9773 | .9778 | .9783 | .9788 | .9793 | .9798 | .9803 | .9808 | .9812 | .9817
2.1 | .9821 | .9826 | .9830 | .9834 | .9838 | .9842 | .9846 | .9850 | .9854 | .9857
2.2 | .9861 | .9865 | .9868 | .9871 | .9875 | .9878 | .9881 | .9884 | .9887 | .9890
2.3 | .9893 | .9896 | .9898 | .9901 | .9904 | .9906 | .9909 | .9911 | .9913 | .9916
2.4 | .9918 | .9920 | .9922 | .9925 | .9927 | .9929 | .9931 | .9932 | .9934 | .9936
2.5 | .9938 | .9940 | .9941 | .9943 | .9945 | .9946 | .9948 | .9949 | .9951 | .9952
2.6 | .9953 | .9955 | .9956 | .9957 | .9959 | .9960 | .9961 | .9962 | .9963 | .9964
2.7 | .9965 | .9966 | .9967 | .9968 | .9969 | .9970 | .9971 | .9972 | .9973 | .9974
2.8 | .9974 | .9975 | .9976 | .9977 | .9977 | .9978 | .9978 | .9980 | .9980 | .9981
2.9 | .9981 | .9982 | .9983 | .9983 | .9984 | .9984 | .9985 | .9985 | .9986 | .9986
3.0 | .9987 | .9987 | .9987 | .9988 | .9988 | .9989 | .9989 | .9989 | .9990 | .9990

## Slide 7: Expected Activity Times and Variance
Activity | Predecessors | Optimistic | Most Probable | Pessimistic | Expected | Variance
A | -- | 7 | 10 | 19 | 11 | 4
B | A | 5 | 8 | 11 | 8 | 1
C | A | 11 | 14 | 20 | 14.5 | 2.25
D | B, C | 8 | 8 | 11 | 8.5 | 0.25
E | C | 4 | 7 | 13 | 7.5 | 2.25
F | D, E | 9 | 12 | 15 | 12 | 1
G | F | 7 | 10 | 19 | 11 | 4
Given these values, CrossChek wants to know:
  What is the expected completion time for the project? 57 days
  What is the probability that the project will be completed in 58 days? 61%. 55 days? 28%

## Slide 8: Inventory Models
CrossChek acts as a distributor for “Joe Buck Signature” footballs. The cost to CrossChek of each football is $20. Demand for this particular type of football varies slightly, but is generally around 100 units per month:
CrossChek estimates that the annual holding cost for each football is 20% of the cost, and a fixed cost of $90 is associated with each order
At what point should we place orders? How much should we order?
Month | Sales | Month | Sales
1 | 104 | 7 | 100
2 | 98 | 8 | 98
3 | 102 | 9 | 104
4 | 101 | 10 | 99
5 | 96 | 11 | 97
6 | 99 | 12 | 102

## Slide 9: Economic Order Quantity Model
Method employed to determine order points and quantities
Assumes constant demand
  Applicable when demand fluctuates slightly
Also assumes entire quantity ordered arrives at a single point in time, when inventory reaches 0

## Slide 10: Other Assumptions
Order quantity is constant
Order cost is constant and independent of quantity
Purchase cost per unit is constant and independent of quantity
Holding cost per unit is constant
No inventory shortages or stock-outs
Lead time for an order is constant
Orders are placed immediately when inventory reaches the reorder point

## Slide 11: Holding Costs
Annual holding cost is the cost of maintaining inventory for one year
Costs include:
  Financing: cost of borrowing or opportunity cost of one’s own money
  Warehouse overhead
  Insurance, taxes, breakage, etc.
Often expressed as a percentage of the value of inventory
  i.e. a percentage of cost of inventory

## Slide 12: CrossChek’s Football Holding Costs
  warehouse cost: 5%
capital cost: 15%
____________________
total holding cost: 20%
i.e. the cost of holding a football for one year
= $20 * 20% = $4

## Slide 13: Ordering Costs
Costs above and beyond the cost of each unit
Fixed, regardless of quantity
Costs include:
  Transportation (i.e. delivery)
  Voucher preparation, processing, postage, receiving, etc.
Expressed as a flat rate

## Slide 14: CrossChek’s Football Ordering Costs
processing: $40
transportation: $50
___________________
total order cost: $90
i.e. each order costs $20 per football, plus $90.

## Slide 15: Total Inventory Cost
Inventory cost = holding cost + ordering cost
Typically expressed as annual figures
Consider the following notation:
  Co: the ordering cost
  Ch: the holding cost per unit
  D: the demand per year
  Q: the quantity to order each time

## Slide 16: Computing Annual Holding Cost
Recall assumptions:
  Demand is constant
  Orders arrive in full when inventory reaches 0

## Slide 17: Computing Annual Holding Cost
Recall assumptions:
  Demand is constant
  Orders arrive in full when inventory reaches 0
Q is the order quantity
Ch is the holding cost per unit

## Slide 18: Computing Annual Holding Cost
Recall assumptions:
  Demand is constant
  Orders arrive in full when inventory reaches 0
Q is the order quantity
Ch is the holding cost per unit
Total holding cost is thus

## Slide 19: Computing Annual Ordering Cost
D is the demand per year
Q is the number of units ordered each time
Number of orders per year is thus

## Slide 20: Computing Annual Ordering Cost
D is the demand per year
Q is the number of units ordered each time
Number of orders per year is thus

## Slide 21: Computing Annual Ordering Cost
D is the demand per year
Q is the number of units ordered each time
Number of orders per year is thus
Co is the ordering cost
The total annual ordering cost for the year is thus

## Slide 22: Computing Annual Ordering Cost
D is the demand per year
Q is the number of units ordered each time
Number of orders per year is thus
Co is the ordering cost
The total annual ordering cost for the year is thus

## Slide 23: Total Annual Inventory Cost
Total annual inventory cost:
  Total annual holding cost + total annual ordering cost:

## Slide 24: Returning to CrossChek’s Problem
Demand:
Total sales for the year: 1200
Holding cost: $4
Ordering cost: $90
Month | Sales | Month | Sales
1 | 104 | 7 | 100
2 | 98 | 8 | 98
3 | 102 | 9 | 104
4 | 101 | 10 | 99
5 | 96 | 11 | 97
6 | 99 | 12 | 102

## Slide 25: Returning to CrossChek’s Problem
Total cost:
What is CrossChek’s annual inventory cost if Q = 50?
  100? 200?

## Slide 26: Costs for Various Q
Q = 50 gives very low holding cost, high ordering cost
Doubling it to Q = 100 doubles holding, cuts ordering in half
  Improves total!
Co = | 90 |  | 
Ch = | 4 |  | 
D = | 1200 |  | 
Q | Total Holding | Total Ordering | Total Cost
50 | 100 | 2160 | 2260
100 | 200 | 1080 | 1280
200 | 400 | 540 | 940
300 | 600 | 360 | 960
400 | 800 | 270 | 1070
500 | 1000 | 216 | 1216

## Slide 27: Costs for Various Q
The more even holding and ordering costs get, the lower the total!
Co = | 90 |  | 
Ch = | 4 |  | 
D = | 1200 |  | 
Q | Total Holding | Total Ordering | Total Cost
50 | 100 | 2160 | 2260
100 | 200 | 1080 | 1280
200 | 400 | 540 | 940
300 | 600 | 360 | 960
400 | 800 | 270 | 1070
500 | 1000 | 216 | 1216

## Slide 28: Computing Optimal Q
The optimal quantity to order can be computed by:

## Slide 29: Computing Optimal Q
The optimal quantity to order can be computed by:

## Slide 30: More Questions
On average, how many times per year will CrossChek order footballs?
What is CrossChek’s average annual holding cost?
What is CrossChek’s average annual ordering cost?
What is CrossChek’s average annual inventory cost?
What is the reorder point (i.e. the level of inventory at which a new order must be placed?
What is the cycle time (i.e. the length of time in between orders)?

## Slide 31: More Questions
On average, how many times per year will CrossChek order footballs?

## Slide 32: More Questions
On average, how many times per year will CrossChek order footballs?
Use
5.17 times per year on average

## Slide 33: More Questions
What is CrossChek’s average annual holding cost?

## Slide 34: More Questions
What is CrossChek’s average annual holding cost?
Use
$464

## Slide 35: More Questions
What is CrossChek’s average annual ordering cost?

## Slide 36: More Questions
What is CrossChek’s average annual ordering cost?
Use
$465

## Slide 37: More Questions
What is CrossChek’s average annual inventory cost?

## Slide 38: More Questions
What is CrossChek’s average annual inventory cost?
Use
$929

## Slide 39: More Questions
What is the reorder point (i.e. the level of inventory at which a new order must be placed?

## Slide 40: Reorder Point
Need to know how long delivery takes
  Say 3 days
  This is known as the lead time
Need to have enough inventory to last 3 days while waiting for shipment
  This is referred to the lead time demand
Thus need to know how many units per day are sold
  How many business days in a year?
  Typically say 250 if open 5 days a week, 300 if 6

## Slide 41: CrossChek
300 business days per year
1200 units sold per year
1200/300 = 4 units sold per day
If lead time for delivery takes 3 days, then the reorder point =
  3 * 4 = 12
i.e. let d be demand per day and m be the lead time in days. The reorder point r is thus
  r = dm

## Slide 42: More Questions
What is the cycle time (i.e. the length of time in between orders)?

## Slide 43: Cycle Time
Number of days between orders
CrossChek:
  Cycle time: CT = 300/5.17 = 58 days